## Overview
ZIBS (in BGZ) | FHIR (datatype/resource) | Mapped | Profiled | Examples? (number) | Checked against ZIB 2017 excl valuesets | Validated? | Notes / Remarks | Issues? FHIR / ZIB | Discussed
Patiënt | Patient |  |  | 1 |  |  |  |  | HL7 WGM 30-03
Nationaliteit | Patient.extension |  |  | 1
BurgerlijkeStaat | Patient.maritalStatus |  |  | 1
Zorgaanbieder | Organization |  |  | 2 |  |  |  |  | HL7 WGM 30-03
Zorgverlener | Practitioner / PractitionerRole |  |  | 1 |  |  |  |  | HL7 WGM 30-03
Contactpersoon | RelatedPerson |  |  | 1
AllergieIntolerantie | AllergyIntolerance |  |  | 1 |  |  |  | Yes
OverdrachtLaboratoriumUitslag | Observation / DiagnosticReport / Specimen |  |  | 18 |  |  | Extension: http://example.org/bodysitecode -> what to do with it?
AlcoholGebruik | Observation |  |  | 1 | V3.1 |  |  | Yes
TabakGebruik | Observation |  |  | 1 |  |  |  | Yes
DrugsGebruik | Observation |  |  | 1 |  |  |  | Yes
Woningsituatie | Observation |  |  | 1 |  |  |  | Yes
Contact | Encounter |  |  | 2 |  |  |  | Yes | HL7 WGM 31-03
OverdrachtConcern | Condition |  |  | 2 |  |  |  | Yes | HL7 WGM 31-03
Overdr.Verrichting | Procedure |  |  | 1 |  |  | Fixed valueset VerrichtingTypeCodelijst to ZIB version 3.0 because of invalid valueset in version 1.2. | Yes | HL7 WGM 31-03
Alert | Flag |  |  | 1 | v3,1 |  |  | Yes | WebEx 24-04
Vaccinatie | Immunization / ImmunizationRecommendation |  |  | 2 |  |  |  | Yes | WebEx 24-04
MedischHulpmiddel | Device / DeviceUseStatement |  |  | 2 |  |  |  | Yes | WebEx 15-05
Betaler | Coverage / Organization / Patient |  |  | 3 |  |  |  | Yes | HL7 WGM 31-03 / WebEx 15-05 / WebEx 29-05
Voedingsadvies | NutritionOrder |  |  | 1 |  |  | Not everything is profiled yet, example can be improved. This whole recource needs attention! gForge #13294 - | Yes | WebEx 15-05 / WebEx 29-05
Funct. OfMentaleStatus | Observation |  |  | 1 |  |  | Need to add an invariant | Yes
Overdr.Gepl.ZorgActiviteit | ProcedureRequest |  |  | 1
Overdr.Gepl.ZorgActiviteit | DeviceUseRequest |  |  | 1
Overdr.Gepl.ZorgActiviteit | ImmunizationRecommendation |  |  | 1 |  |  | Similar as ZIB Vaccination
Overdr.Gepl.ZorgActiviteit | Appointment |  |  | 1
Overdr.Gepl.ZorgActiviteit | MedicationRequest | [5 empty] | Similar as MedicationAgreement
BehandelAanwijzing | Consent |  |  | 1 |  |  |  | Yes | HL7 WGM 31-03 / WebEx 29-05
Wilsverklaring | Consent |  |  | 1 |  |  |  | Yes | WebEx 29-05
VitalSigns / Zelfmetingen
Bloeddruk | Observation |  | n/a |  |  |  | http://www.hl7.org/fhir/STU3/observation-vitalsigns.html | Yes
Lichaamsgewicht | Observation |  | n/a |  |  |  | http://www.hl7.org/fhir/STU3/observation-vitalsigns.html
Lichaamslengte | Observation |  | n/a |  |  |  | http://www.hl7.org/fhir/STU3/observation-vitalsigns.html
Lichaamstemperatuur | Observation |  | n/a |  |  |  | http://www.hl7.org/fhir/STU3/observation-vitalsigns.html
O2Saturatie | Observation |  | n/a |  |  |  | http://www.hl7.org/fhir/STU3/observation-vitalsigns.html
Polsfrequentie | Observation |  | n/a |  |  |  | http://www.hl7.org/fhir/STU3/observation-vitalsigns.html
Medicatieproces 9
Medication | Medication | [5 empty] | No formal mapping in profile yet
MedicationUsage | MedicationStatement |  |  | 1 |  |  | No formal mapping in profile yet
MedicationAgreement | MedicationRequest |  |  | 1 |  |  | No formal mapping in profile yet
MedicationDispense | MedicationDispense |  |  | 1 |  |  | No formal mapping in profile yet
MedicationDispenseRequest | MedicationRequest |  |  | 1 |  |  | No formal mapping in profile yet
DosageInstructions | Dosage (datatype) | [5 empty] | No formal mapping in profile yet
AdministrationSchedule | Timing (datatype) | [5 empty] | No formal mapping in profile yet
MedicationAdministration | MedicationAdministration | [5 empty] | No formal mapping in profile yet
MedicationAdministrationAgreement | MedicationRequest | [5 empty] | No formal mapping in profile yet

## Issues
ZIB | ID | Description | Status | Resolution
AlcoholGebruik | ZIB-470 | Terminologiekoppeling Alcoholgebruik | In autorisatie | Unresolved
Alert | ZIB-438 | Bouwsteen Alert aanpassen om het probleem als reden van het alert door te geven zonder dat het naar het concept concern wordt verwezen. | Afgewezen | Won't Fix | Door de herdefinitie van de bouwsteen concern is dit issue niet meer actueel.
Alert | ZIB-526 | Toevoegen EindDatum bij zibs die ook BeginDatum kennen | Toekomst | Future
Alert | ZIB-591 | Uitbreiding references (naast Conditie::Concern) | In intake | Unresolved
Alert | ZIB-592 | Constraint in keuze box verwijderen | In intake | Unresolved
Alert | ZIB-593 | Herzie Alert codelijsten | In intake | Unresolved
AllergyIntolerance | #10369 | Extend AllergyIntoleranceCertainty with Unknown, Ruled Out, and Possible | Published | Add the term "unknown" to the AllergyIntolerance.reaction.certainty code set. If other terms are desired for use in a specific setting, recommend the use of an extension or alternatively a profile.
AllergyIntolerance | #13459 | AllergyIntolerance.reaction core extension certainty is insufficient |  | We will ignore the core extension for certainty and create our own
Betaler | ZIB-582 | ZIB betaler: banknaam onnodig verplicht | In realisatie | Unresolved | Cardinaliteit gewijzigd van 1 naar 0..1
Consent | #13313 | Add note / comment to Consent | Triaged | Awaiting specific use case not currently covered.
Consent | #13358 | Make Policy and PolicyRule a codeableconcept instead of URI | Triaged | Persuasive with Mod: Change example from URL for Opt-in/Opt-out to acual samples of URIs for regulations to better demostrate the use case.
Consent | #13359 | change datatype of consent.reason.code from coding to codeableconcept | Triaged
Consent | #13360 | Remove invariant “Either a Policy or PolicyRule” | Triaged
Consent | #13361 | Add option to allow for sepcifying wether a consent was verified by the patient or his/her family | Resolved - Change required | Narrative between this and the agent element to avoid duplication
Contact | #13155 | Encounter.serviceProvider use and description not clear | Resolved - Change required | The description of the serviceProvider field on Encounter will be updated to be "The organization (facility) responsible for this encounter"
Covarage | #13475 | Coverage needs a place to capture payor bank details | Submitted
DrugsGebruik | ZIB-475 | Terminologiekoppeling Drugsgebruik | In realisatie | Unresolved
FunctioneleOfMentaleStatus | ZIB-570 | Terminologiekoppeling FunctioneleOfMentaleStatus | Afgewezen | Won't Fix
Immunization | #13290 | Immunization – Organization reference? | Resolved - Change required | Motion: expand practioner.actor to include organization along with practitioner, add onBehalfOf and rename the element from practioner to performer. This will bring us better in line with Event and MedicationAdministration.
LivingSituation | ZIB-604 | Naam wijzigen van Woonsituatie naar Woonvoorziening | In intake | Unresolved
MedicalAid | ZIB-605 | Naam MedischHulpmiddel veranderen in bijvoorbeeld MedischHulpmiddelGebruik | In intake | Unresolved
MedischHulpmiddel | #12799 | DeviceUseStatement indication reference | Resolved - Change required | Plan to align with Workflow event pattern in STU4 and will have a partOF element or extension to meet this use.
MedischHulpmiddel | #12800 | DeviceUseStatement healthcareProvider reference | Resolved - Change required | Plan to align with Workflow event pattern in STU4 and will have a partOF element or extension to meet this use.
MedischHulpmiddel | ZIB-568 | Example Instances niet correct | In realisatie | Unresolved
Meerdere ZIBS | ZIB-598 | Het 'locatie' element in referentie concepten naar de ZIB Zorgaanbieder zijn verwarrend | In intake | Unresolved
Nationaliteit | ZIB-599 | Cardinaliteit Nationaliteit van 0..1 naar 0..* | In intake | Unresolved
NutritionOrder | #13294 | Add a note element to NutritionOrder | Resolved - Change required | add note element to resource as proposed (also part of Workflow alignment)
OverdrachtConcern | #13201 | Condition Xpath constraint con-4 is not correct | Applied | 1-remove abatementBoolean 2-if abatement is populated, then clinicalStatus must be resolved, remission, inactive 3-if no abatement, then any clinical status is acceptable
Patient | ZIB-349 | VIPIndicator uit bouwsteen OverdrachtPatient verwijderd | In intake | Unresolved
Patient | ZIB-597 | Nummersoort en EmailSoort niet verplicht | In intake | Unresolved
Payor | #12685 | Linking of Accounts required | Triaged | This was discussed and in concept agree, but we would like more detail on the usage, potential types, and impact on the linked to account. (e.g. Does the balance change?)
Procedure | #13159 | Add a reference to practitionerRole in procedureRequest | Triaged | Auto-deferred
TabakGebruik | ZIB-562 | Terminologiekoppeling Tabakgebruik | In realisatie | Unresolved
Vaccination | ZIB-567 | Context reference Zorgaanbieder ontbreekt | In analyse | Unresolved
Vaccination | ZIB-594 | Granulariteit ZIB Vaccinatie – GewensteDatumHervaccinatie | In intake | Unresolved
Vaccination | ZIB-595 | Informatiebron vaccinatie | Afgewezen | Won't Fix | Bron van de informatie is een basiselement van de zibs en dus in alle zibs aanwezig. We gaan dit nog beter communiceren in de ZIB's
Vital Signs | #13407 | VitalSigns profile > BloodPressure incomplete according to panel definition | Submitted
VoedingAdvies | #13415 | Merge NutritionOrder texture and fluidConsistencyType | Submitted
VoedingAdvies | #13475 | NutritionOrder materials used or needed to perform the order | Submitted
Woningsituatie | ZIB-561 | Terminologiekoppeling Woonsituatie | In realisatie | Unresolved
Zorgaanbieder | #9824 | Organization.active description is not clear | Resolved | Description in FHIR updated in STU3
Zorgaanbieder | ZIB-452 | AfdelingSpecialisme hoort niet thuis in deze ZIB | In analyse | After initial rejection of the issue, it has been reopened with new supporting arguments
Zorgaanbieder | ZIB-583 | Cardinaliteit OrganisatieNaam | In realisatie | Unresolved | Cardinaliteit Organisatienaam gewijzigd van 1 naar 0..1
Zorgverlener | ZIB-501 | Zorgverlener zou meerdere rollen moeten ondersteunen | Afgewezen | The ZIB issue is rejected, but because of PractitionerRole in FHIR STU3 is it no longer an issue
Zorgverlener | ZIB-502 | ZorgverlenerRol hoort niet thuis bij Zorgverlener | Afgewezen | The ZIB issue is rejected, but because of PractitionerRole in FHIR STU3 is it no longer an issue
TreatmentInstruction | #13540 | Treatment Instruction - Consent use case | Submitted